## Gantt
Pre-Populated Patient Intake Forms | [46 empty] | Legend:
[47 empty] | On Track |  |  |  |  | Low Risk |  |  |  |  | Med Risk |  |  |  |  | High Risk |  |  |  |  | Unassigned
|  |  | Project Start Date: | 2020-09-23
|  |  | Display Week: | 1 |  | September | [13 empty] | October | [27 empty] | November
 | time axis 2020-09-21 to 2020-11-27
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
Milestone Description | Category | Assigned To | Progress | Start | No. Days | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
Sprint 3 | On Track
Develop screen prototypes | Med Risk | Parul | 100% | 2020-09-23 | 6
Flesh out solution architecture | Med Risk | Marouane | 100% | 2020-09-23 | 6
Sprint 4 | On Track
Setup backend code skeleton | Med Risk | Marouane | 100% | 2020-10-05 | 10
Setup frontend code skeleton | Med Risk | Anthony | 100% | 2020-10-05 | 10
Setup deployment infrastructure | High Risk | Daniel | 100% | 2020-10-05 | 10
Sprint 5
Implement main screen mockup | On Track |  | 100% | 2020-10-19 | 9
Implement FHIR service invoker | Low Risk |  | 100% | 2020-10-19 | 9
Integrate main screen with FHIR service invoker | On Track |  | 100% | 2020-10-28 | 3
Test Plan, including scenario documentation | On Track |  | 100% | 2020-10-19 | 8
Sprint 6
Implement main screen | High Risk |  | 90% | 2020-11-02 | 9
Implement backend services | High Risk |  | 90% | 2020-11-02 | 9
Update app using mentor's feedback | Med Risk |  | 100% | 2020-11-02 | 6
Sprint 7
Implement UI validations & constraints. | Med Risk |  | 30% | 2020-11-16 | 8
Implement POST APIs | High Risk |  | 100% | 2020-11-16 | 8
QA/ add more tests | Med Risk |  | 100% | 2020-11-16 | 8
Integrate End to End Flow | Med Risk |  | 100% | 2020-11-21 | 6
Update documentation | Low Risk |  | 100% | 2020-11-23 | 5
Sprint 8
Deployment testing | Low Risk |  | 100% | 2020-11-30 | 5
Presentation and video | Low Risk |  | 100% | 2020-11-30 | 5
To add more data, Insert new rows ABOVE this one

## About
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks description, select a category of Goal, Milestone, On Track, Low Risk, Med Risk, High Risk, Progress as a percent of task completion, a Start Date and Number of days to complete the task. The Gantt chart fills in and is color coded to help distinguish the various categories. Change the display week number to change the timeline view. Insert new tasks by inserting new rows.
Guide for Screen Readers
There are 2 worksheets in this workbook. Gantt Chart About The instructions for each worksheet are in the A column starting in cell A1 of each worksheet. They are written with input messages. Each step guides you through the information in that row. Each subsequent step continues in cell A2, A3, and so on, unless otherwise explicitly directed. For example, instruction text might say "continue to cell A6" for the next step. To remove these instructions from the worksheet, go to Data > Data Tools > Data Validation > Input Message and delete them.
This is the last instruction in this worksheet.